## Sheet1
Feature
Task Tab -> | Expected due date | tasks as a list of items | color indication of progress | create a task
Recurring Tasks Tab -> | track recurring tasks | create recurring tasks
Notebook Tab -> | notetaking | create note | edit note
Perfomance Tab -> | report on how well user makes deadlines | track past due occurrences
progress checks on long term tasks
reminders
User stories
Basic Features | Priority | Status | Person Assigned
As a user, I need a task tab so that I can create, delete, and view tasks. | High | Completed | Darren
As a user, I need a new task button so that we can create new tasks. | High | Completed | Darren
As a developer, I need to implement the new tab UI. | High | Completed | Khaled
As a user, I need a view for modifying tasks so that I can edit tasks. | Medium | Completed | Khaled
As UI engineer, I need a wireframe of the entire app. | High | Completed | Wayne
As a user, I need a way to cancel the creation of tasks, so that I can return to the task list. | Medium | Completed | Darren
As a user, I need a template on the new task page with basic task information. | High | Completed | Darren
As a user, I need a button to create new tasks. | Medium | Completed | Darren
As a user, I need a notebook tab so that I can create notes. | High | Completed | Khaled
As a user, I need a performance tab so that I can measure my preformance metrics. | High | Completed | Wayne
As a developer, we create excel file with the database file so that we have a visual representation of the db. | High | Completed | Kyle
As a developer, we need a task table set up in SQL light so that we can save and delete data for tasks. | High | Completed | Darren
As a developer, we need a notebook table set up in SQL light so that we can save and delete data for notes. | High | Completed | Khaled
As a developer, we need an algorithm for determining the performance metrics. | Medium | Completed | Ameer
As a UI designer, we need an app icon. | High | Completed | Rammy and Wayne
As a user, I need a create new note button, | High | Completed | Khaled
As a user, I need a create note view, so that I can create a new note | High | Completed | Ameer
As a user I need a delete note button so that I can delete notes. | Medium | Completed | Khaled and Ameer
As a user, I need the progress bar changes to green when the task is at 100% completion so that I have an improved visual representation | Low | Completed | Darren
As a user, I need the number of completed tasks, overdue tasks, and the average time tasks are late. | High | Completed | Wayne
As a user , I need a performance graph on the performance tab, so that I can view performance data | High | Completed | Wayne
As a user, I need an alert that lets me know when I'm leaving the create task page if the form is dirty. | Low | Backlog
As a user, I need a reacurring task option on the task tab so that I can create reacurring tasks. | Low | Backlog
Current goal: Polishing up the final version of the app. Creating test cases.
Misc/ Security/ Database
As a developer, I need to check the login status on each state change.
As a developer, I need a task table so that I can track tasks.
As a developer, I need a user table so that we can track user information.
Note on A12: Feel free to add to these, this should be a sufficient start, and these will take at least a week. -Kyle Ziegler