## Sheet1
Feature
Task Tab -> | Expected due date | tasks as a list of items | color indication of progress | create a task
Recurring Tasks Tab -> | track recurring tasks | create recurring tasks
Notebook Tab -> | notetaking | create note | edit note
Perfomance Tab -> | report on how well user makes deadlines | track past due occurrences
progress checks on long term tasks
reminders
User stories
Basic Features | Priority | Status | Person Assigned
As a user, I need a task tab so that I can create, delete, and view tasks. | High | Completed | Darren
As a user, I need a new task button so that we can create new tasks. | High | Completed | Darren
As a user, I need an alert that lets me know when I'm leaving the create task page if the form is dirty. | Low |  | Darren
As a developer, I need to implement the new tab UI. | High |  | Khaled
As a user, I need a view for modifying tasks so that I can edit tasks. | Medium
As UI engineer, I need a wireframe of the entire app. | High |  | Wayne
As a user, I need a way to cancel the creation of tasks, so that I can return to the task list. | Medium
As a user, I need a template on the new task page with basic task information. | High | Completed | Darren
As a user, I need a button to create new tasks. | Medium | Completed | Darren
As a user, I need a reacurring task option on the task tab so that I can create reacurring tasks. | Medium
As a user, I need a notebook tab so that I can create notes. | High
As a user, I need a performance tab so that I can measure my preformance metrics. | High
As a developer, we create excel file with the database file so that we have a visual representation of the db. | High |  | Kyle
As a developer, we need a task table set up in SQL light so that we can save and delete data for tasks. | High
As a developer, we need a notebook table set up in SQL light so that we can save and delete data for notes. | High
As a developer, we need an algorithm for determining the performance metrics. | Medium |  | Ameer
As a UI designer, we need an app icon. | High |  | Rammy
Misc/ Security/ Database
As a developer, I need to check the login status on each state change.
As a developer, I need a task table so that I can track tasks.
As a developer, I need a user table so that we can track user information.
Note on A12: Feel free to add to these, this should be a sufficient start, and these will take at least a week. -Kyle Ziegler