## Sheet1
Tab | Feature | User Story # (slide #) | Start Date | Expected End Date
Task Tab | Create Task | 1 | 2016-01-25 | 2016-01-27
Task Tab | Create recurring Task | 2 | 2016-01-28 | 2106-01-31
Task Tab | See tasks as list | 3 | 2016-02-01 | 2016-02-01
Task Tab | Indicate progress on task | 4 | 2016-02-02 | 2016-02-02
Task Tab | Sort tasks | 5 | 2016-02-03 | 2016-02-05
Task Tab | Delete task | 6 | 2016-02-06 | 2016-02-06
Task Tab | Delete recurring task | 7 | 2016-02-07 | 2016-02-07
Task Tab | Divide task into subtasks | 8 | 2016-02-08 | 2016-02-10
Task Tab | Track progress on recurring task | 9 | 2016-02-11 | 2016-02-12
Tab | Feature | User Story # (slide #) | Start Date | Expected End Date
Notebook Tab | Create a note | 10 | 2016-02-13 | 2016-02-15
Notebook Tab | Edit a note | 11 | 2016-02-16 | 2016-02-17
Notebook Tab | Delete a note | 12 | 2016-02-18 | 2016-02-18
Tab | Feature | User Story # (slide #) | Start Date | Expected End Date
Perfomance Tab | Track past due occurrences | 13 | 2016-02-19 | 2016-02-23
Perfomance Tab | Track how well user meets deadlines | 14 | 2016-02-24 | 2016-02-26
Perfomance Tab | Share progress on facebook | 15 | 2016-02-27 | 2016-03-02
Tab | Feature | User Story # (slide #) | Start Date | Expected End Date
General | Reminders about tasks | 16 | 2016-03-03 | 2016-03-04
General | Reports on long term tasks | 17 | 2016-03-05 | 2016-03-07